## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | RoboBoat Timeline
Enter Company Name in cell B2. | UAV Addition to ASV | [9 empty] | 1 | Planed Duration | [5 empty] | 1 | Desired End |  |  |  |  | 1 | In Progress | [5 empty] | Off Track | [5 empty] | Completed |  |  |  |  | Determine |  |  |  |  | Hardware |  |  |  |  | Software |  |  |  |  | Practice |  |  |  | Drone Movement | [6 empty] | Mapping |  |  |  | Documents/Presentations
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Joseph Stevens, Brennan Moeller, Nathan Madsen, Ben Willis |  | Final Project Start: |  |  | 2021-01-19
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | Display Week: |  |  | 1 |  |  |  |  | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-01-18 to 2021-07-18
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PRIORITY (1-5) | ASSIGNED TO | TASK TITLE | PROGRESS | START | DESIRED END | PROJECTED END | DAYS | time axis 2021-01-18 to 2021-07-18
| Total | 1=NOT IMPORTANT AT THIS TIME 5=VERY IMPORTANT |  |  | 70.07%
| Sponsor TODOs |  |  |  | 85.71%
| Check old ASV Batteries | N/A | Joseph/Brennan |  | 100% | 2021-01-27 | 2021-01-28 | 2021-01-30
| Find non-Ebay for Futaba reciever | N/A | Joseph |  | 100% | 2021-01-27 | 2021-01-28 | 2021-01-30
| Spin up ROS node for the Rpi Camera | N/A | Brennan |  | 100% | 2021-01-27 | 2021-02-01 | 2021-02-06
| Create Block Diagram for WiFi Network | N/A | Brennan |  | 100% | 2021-01-27 | 2021-02-05 | 2021-02-14
| Check for Futaba back compatiability | N/A | Joseph |  | 100% | 2021-01-27 | 2021-02-05 | 2021-02-08
| Check simulated weight vs. real weight | N/A | Team, Joe, Brennan |  | 100% | 2021-02-14 | 2021-02-22 | 2021-02-22
| Spin up a GitHub Webpage | 5 | Team? |  | 0% | 2021-02-15 | 2021-05-14 | 2021-05-23
| - Figure out where we should have tabs for another "page" and where we should place all the information. Have this as the plan of action for how to attack this website | 5 | Ben |  | 0% | 2021-04-18 | 2021-04-19 | 2021-04-22
| - Add in last teams webpage or add a tab for them on this one | 5 |  |  | 0%
| - Add description and pictures for ASV | 5 |  |  | 0%
| - Add description and pictures for UAV | 5 |  |  | 0%
| - Add movies for ASV | 5 |  |  | 0%
| - Add in a spot for Labelbox | 5 |  |  | 0%
| - Add in a spot for Team Introduction | 5 |  |  | 0%
| - Add in a spot for TDR(s) | 5 |  |  | 0%
| - Add in a spot for Reason for being in the RoboBoat Competition at homepage | 5 |  |  | 0%
| - Add movie fails for UAV and specify why they are a "failed" version of the product | 5 |  |  | 0%
| - UAV Desription: Talk about reasoning for UAV | 5 |  |  | 0%
| - UAV Desription: Talk about Accompshments in product design | 5 |  |  | 0%
| - UAV Desription: Talk about Accompshments in simulation | 5 |  |  | 0%
| - UAV Desription: Talk about Goal for future teams | 5 |  |  | 0%
| - UAV Desription: Talk about Goal for this project | 5 |  |  | 0%
| RTK |  |  |  | 0%
| - What can we do to get down to half a foot (Currently in two and a half to three hours we were able to get down to 1.9ft) |  |  |  | 0%
| - Can we dial it in using U-Center to set up the base station and publish the data. Unkown if it needs to be published with Qground |  |  |  | 0%
| NAVIO 2 |  |  |  | 0%
| - Figure out how to interface with it to just use RPI to just read the data from the sensors, but not use the actual mission planner. Just use it to read all that data and just publish it to ROS |  |  |  | 0%
| Robot_Localization |  |  |  | 0%
| - Package, just learn how to interface with it |  |  |  | 0%
| ROS_Navigation |  |  |  | 0%
| - Package, just learn how to interface with it |  |  |  | 0%
| SMACH |  | Brennan |  | 0%
| - Put together a list of states for the Robot to be in throughout the comeptition |  | Brennan |  | 0%
| - Working through task by task. Thinknig about the whole state machine |  | Brennan |  | 0%
| Left to Determine |  |  |  | 100%
| Determine what Receiver/ RC Controller to obtain | N/A | Joseph | Determine | 100% | 2021-01-20 | 2021-01-23 | 2021-01-25
| Determine if Tara Stereo Camera is necessary | N/A | Team | Determine | 100% | 2021-01-25 | 2021-02-05 | 2021-02-08 | 15 | 12
| Determine Router and Switch to get for ASV | N/A | Brennan | Determine | 100% | 2021-01-23 | 2021-02-05 | 2021-02-14
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Hardware Installation/Test |  |  |  | 95.54%
| Put together Installation Instructions for PX4, RTK, Motors, ESC, etc. on GitHub | N/A | Ben | Hardware | 100% | 2020-12-29 | 2021-01-11 | 2021-01-13 | 16 | 14
| Test Raspberry Pi 4 before installation | N/A | Team |  | 100% | 2021-01-23 | 2021-01-24 | 2021-01-25
| Test Pi Cam with Rasberry Pi 4 | N/A | Team |  | 100% | 2021-01-23 | 2021-01-24 | 2021-01-25
| Test PX4 Pixhawk Qground Control | N/A | Team |  | 100% | 2021-01-23 | 2021-01-24 | 2021-01-25
| Test PX4 connectivity with GPS | N/A | Team |  | 100% | 2021-01-23 | 2021-01-24 | 2021-01-25
| Test RC Controller connectivity with PX4 | N/A | Team |  | 100% | 2021-01-23 | 2021-01-24 | 2021-01-25
| Test Raspberry Pi 4 is getting power from PX4 | N/A | Team |  | 100% | 2021-01-25 | 2021-01-27 | 2021-02-01
| Test ESC/Power Module/Battery/Motor connection | N/A | Team |  | 100% | 2021-01-25 | 2021-01-27 | 2021-02-01
| Test RTK connectivity and function with PX4 before installation | N/A | Team |  | 100% | 2021-01-25 | 2021-02-27 | 2021-03-01
| Manufacture mount to stack PX4 Pixhawk/Raspberry Pi 4/RTK *(DJI Forward)* | N/A | Ben |  | 100% | 2021-02-01 | 2021-02-26 | 2021-02-28
| Manufacture camera and lidar mount | N/A | Nathan |  | 100% | 2021-02-02 | 2021-02-26 | 2021-02-28
| Manufacture Mount for Power Module | N/A | Ben |  | 100% | 2021-02-03 | 2021-02-26 | 2021-02-28
| Install Motor ESC | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Install PX4 Pixhawk | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
| Install Battery | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
| Install Raspberry PI | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
| Isntall Power Module | N/A | Team |  | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05
| Install Receiver | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05
| Install RTK Breakout Board | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
| Install Interface Cable for RTK to Antenna | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
| Install RTK Antenna | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-28 | 2021-03-05 | 30 | 25
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Assemble F450 Drone Frame | N/A | Team | Hardware | 100% | 2021-02-04 | 2021-02-21 | 2021-03-10 | 35 | 18
| Power up drone and test components | 5 | Ben/Brennan |  | 75% | 2021-02-07 | 2021-03-13 | 2021-03-15
| Install Propeller Shrouds | N/A | Team | Hardware | 100% | 2021-02-12 | 2021-02-24 | 2021-03-05 | 22 | #REF!
| Create mount for Raspberry Pi Camera | N/A | Nathan |  | 100% | 2021-02-12 | 2021-02-16 | 2021-03-05
| Install Raspberry PI Camera | N/A | Team | Hardware | 100% | 2021-02-22 | 2021-02-26 | 2021-03-05 | 12 | 5
| Install Parts to make Drone Positively Buoyant | N/A | Team | Hardware | 100% | 2021-03-07 | 2021-03-12 | 2021-03-21 | 15 | 6
| Install Object Obtaining Device | 1 | Team | Hardware | 0% | 2021-03-07 | 2021-03-12 | 2021-04-01 | 26 | 6
| Install Enclosure on ASV | N/A | Team | Hardware | 100% | 2021-03-10 | 2021-04-20 | 2021-04-29 | 51 | 42
| Install Mounting Plate for Electronics on ASV | 4 | Team | Hardware | 0% | 2021-04-01 | 2021-04-20 | 2021-04-29
| Install Lip on ASV Box | 2 | Team | Hardware | 0% | 2021-04-01 | 2021-04-20 | 2021-04-29
| Install Electronics on ASV | 4 | Team | Hardware | 0% | 2021-04-01 | 2021-04-20 | 2021-04-29 | 29 | 20
| Install RTK to ASV | 4 | Team | Hardware | 0% | 2021-04-01 | 2021-04-20 | 2021-04-29 | 29 | 20
| Install Raspberry Pi 4 on ASV | 4 | Team | Hardware | 0% | 2021-04-01 | 2021-04-20 | 2021-04-29 | 29 | 20
| Hardware Development/Creation |  |  |  | 74.17%
| Create a model mount to stack PX4 Pixhawk/Raspberry Pi 4/RTK *(DJI Forward)* | N/A | Ben |  | 100% | 2021-01-27 | 2021-02-01 | 2021-02-03
| Create a model with camera and lidar mount | N/A | Nathan |  | 100% | 2021-01-27 | 2021-02-01 | 2021-02-03
| Create a model Mount for Power Module | N/A | Ben |  | 100% | 2021-01-27 | 2021-02-01 | 2021-02-03
| Create Drone Stand/ Flotation Device Model | N/A | Joseph & Nathan | Hardware | 100% | 2021-01-29 | 2021-02-15 | 2021-02-22 | 25 | 18
| Create DIN Rail Setup for ASV | N/A | Brennan | Hardware | 100% | 2021-01-29 | 2021-02-20 | 2021-02-27 | 30 | 23
| Create Propeller Shrouds | N/A | Joseph & Nathan | Hardware | 100% | 2021-01-29 | 2021-02-28 | 2021-03-05 | 36 | 31
| Design System for Drone to be Positively Buoyant | N/A | Joseph | Hardware | 100% | 2021-01-29 | 2021-03-04 | 2021-03-06 | 37 | 35
| Create all Enclosures | N/A | Team |  | 100% | 2021-02-07 | 2021-02-26 | 2021-02-28
| Make enclosure for Raspberry PI water resistant to IP34 standards | N/A | Team | Hardware | 100% | 2021-02-15 | 2021-03-12 | 2021-03-17 | 31 | 26
| Make enclosure for Raspberry PI camera water resistant to IP34 standards | N/A | Team | Hardware | 100% | 2021-02-15 | 2021-03-12 | 2021-03-17 | 31 | 26
Sample phase title block | Make enclosure for stereo camera water resistant to IP23 standards | 2 | Team | Hardware | 90% | 2021-02-15 | 2021-03-12 | 2021-03-17 | 31 | 26
| Determine if team should laser cut carbon fiber plates | N/A | Brennan/Ben/Joseph |  | 100% | 2021-02-23 | 2021-02-23 | 2021-02-23
| Call architecture department in Fletcher to see about using laser cutter | N/A | Joseph |  | 100% | 2021-02-24 | 2021-02-25 | 2021-02-26
| Test Drone Buoyancy | N/A | Joseph |  | 100% | 2021-03-20 | 2021-04-09 | 2021-04-21
| Create the Object Obtaining Device | 1 | Team | Hardware | 0% | 2021-03-20 | 2021-04-09 | 2021-04-21 | 33 | 21
| Create Lip on Enclosure for ASV | 2 | Team | Hardware | 0% | 2021-03-20 | 2021-04-09 | 2021-04-21 | 33 | 21
| Develop a way for Drone to know where it is supposed to land (ARUCO Tags?) | 2 | Team | Hardware | 0% | 2021-03-20 | 2021-04-09 | 2021-04-21
| Software Installation |  |  |  | 100%
| Install Debian Buster/ ROS on Raspberry PI's | N/A | Team | Software | 100% | 2021-01-19 | 2021-01-29 | 2021-02-03 | 16 | 11
| Install MAVROS on Raspberry PI | N/A | Brennan | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Install Package to mimic F450 | N/A | Brennan/Ben | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Install qGround Control on Main Computer | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Update software in PX4 throught qGround Control on Main Computer | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Install MAVROS on Main Computer | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Install Noetic on Main Computer | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Update RTK Software | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18
| Install Noetic on ASV's Raspberry Pi | N/A | Brennan | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Install Chosen 3-D Mapping Algorithm on TX2 | N/A | Brennan | Software | 100% | 2021-01-26 | 2021-02-28 | 2021-03-01 | 35 | 34
| Software Development/Creation |  |  |  | 67.79%
| Create Basic Wiring Diagrams for Drone | N/A | Nathan | Software | 100% | 2020-12-29 | 2021-01-12 | 2021-01-13 | 16 | 15
| Create Images Buoys via Blender | N/A | Joseph | Software | 100% | 2021-01-12 | 2021-03-07 | 2021-03-14 | 62 | 55
| Create First Draft of Mount for ASV | N/A | Brennan | Software | 100% | 2021-01-19 | 2021-01-22 | 2021-01-24
| Set up rover and base for RTK system | N/A | Brennan/Joseph/Ben | Software | 100% | 2021-01-26 | 2021-02-26 | 2021-02-28
| Set up Offboard Control on QGround Control | N/A | Team | Software | 100% | 2021-01-26 | 2021-02-12 | 2021-02-18 | 24 | 18
| Create simulator in Rotors for F450 | 5 | Brennan, Ben |  | 98% | 2021-02-20 | 2021-03-15 | 2021-04-01
| - Insert F450 Frame into RotorS | 5 | Brennan, Ben |  | 100% | 2021-02-20 | 2021-03-15 | 2021-04-01
| - Tune the F450 PID Controller for RotorS | 5 | Brennan, Ben |  | 100% | 2021-02-20 | 2021-03-15 | 2021-04-01
| - Add OAK-D to F450 RotorS | 5 | Brennan, Ben |  | 100% | 2021-02-20 | 2021-03-15 | 2021-04-01
| - Add RPI Camera to RotorS | 5 | Brennan, Ben |  | 100% | 2021-02-20 | 2021-03-15 | 2021-04-01
| - Add LiDAR to F450 RotorS | 5 | Brennan, Ben |  | 90% | 2021-02-20 | 2021-03-15 | 2021-04-01
| Create a way to have Drone sending data over to ASV | N/A | Team | Software | 100% | 2021-03-01 | 2021-03-12 | 2021-03-14 | 14 | 12
| Determine Electronic/Wiring Layout for Enclosure on ASV | N/A | Brennan | Software | 100% | 2021-03-01 | 2021-03-20 | 2021-03-28 | 28 | 20
| Test RTAB-Map via docker image/compose file on the TX2 | ? | Brennan |  | 0% | 2021-03-07 | 2021-03-20 | 2021-03-28
| Create a way to have Drone understand when to Drop off/Pick up and object | 1 | Team | Software | 0% | 2021-03-10 | 2021-03-26 | 2021-03-30 | 21 | 17
| Collect & store data from Oak-D through ROS | ? | Nathan |  | 0% | 2021-03-25 | 2021-03-29 | 2021-03-31
| Get Pipeline for Rendering Blender Images up and running | 1 | Joseph |  | 0% | 2021-03-17 | 2021-03-28 | 2021-04-01
| Finish Blender Scene for Entire Course | 1 | Joseph |  | 0% | 2021-03-28 | 2021-04-04 | 2021-04-08
| Create a Machine Learning Algorithm for Buoys | 1 | Joseph | Software | 0% | 2021-04-04 | 2021-04-15 | 2021-04-18 | 15 | 12
| Practice IRL w/ Turtlebot |  |  |  | 100%
| Turtlebot Avoiding Obstacles | N/A | Brennan/Ben | Practice | 100% | 2020-12-29 | 2021-01-13 | 2021-01-13 | 16 | 16
| Turtlebot Moving Autonomously | N/A | Brennan/Ben | Practice | 100% | 2020-12-29 | 2021-01-13 | 2021-01-13 | 16 | 16
| Turtlebot Moving Progromatically | N/A | Brennan/Ben | Practice | 100% | 2020-12-29 | 2021-01-13 | 2021-01-13 | 16 | 16
| Turtlebot Creating a Map | N/A | Brennan/Ben | Practice | 100% | 2020-12-29 | 2021-01-13 | 2021-01-13 | 16 | 16
| Turtlebot Creates a Map via Waypoints | N/A | Brennan | Practice | 100% | 2020-12-29 | 2021-01-13 | 2021-01-13
| Adding Another Camera to Turtlebot for Object Detection | N/A | Brennan/Ben | Practice | 100% | 2021-01-08 | 2021-01-13 | 2021-01-13 | 6 | 6
| Manipulate Turtlebot to spell out ULL | N/A | Brennan | Practice | 100% | 2021-01-08 | 2021-01-13 | 2021-01-13
| Autonomous/Manual Movement |  |  |  | 0.5455%
| Actual Drone Lift Off via RC Controller | 5 | Ben/Brennan/Joe | Drone Movement | 2% | 2021-02-09 | 2021-03-24 | 2021-03-26 | 46 | 44
| Actual Drone Moves via RC Controller | 5 | Ben/Brennan/Joe | Drone Movement | 2% | 2021-02-09 | 2021-03-24 | 2021-03-26 | 46 | 44
| Actual Drone Lands via RC Controller | 5 | Ben/Brennan/Joe | Drone Movement | 2% | 2021-02-09 | 2021-03-24 | 2021-03-26 | 46 | 44
| Actual Drone Fully Autonomous | 3 | Team | Drone Movement | 0% | 2021-02-14 | 2021-04-09 | 2021-04-21 | 67 | 55
| Actual Drone Lifts Off Autonomously | 5 | Team | Drone Movement | 0% | 2021-02-14 | 2021-04-09 | 2021-04-21 | 67 | 55
| Actual Drone Lands Autonomously | 5 | Team | Drone Movement | 0% | 2021-02-14 | 2021-04-09 | 2021-04-21 | 67 | 55
| Actual Drone Moves Autonomously via RTK Coordinates | 5 | Team | Drone Movement | 0% | 2021-02-14 | 2021-04-09 | 2021-04-21 | 67 | 55
| Actual Drone Lifts off the ASV Autonomously on Land | 3 | Team | Drone Movement | 0% | 2021-03-14 | 2021-04-09 | 2021-04-21 | 39 | 27
| Actual Drone Lands on the ASV Autonomously on Land | 3 | Team | Drone Movement | 0% | 2021-03-14 | 2021-04-09 | 2021-04-21 | 39 | 27
| Actual Drone Lifts off the ASV Autonomously on Water | 3 | Team | Drone Movement | 0% | 2021-03-22 | 2021-04-19 | 2021-04-28 | 38 | 29
| Actual Drone Lands on the ASV Autonomously on Water | 3 | Team | Drone Movement | 0% | 2021-03-22 | 2021-04-19 | 2021-04-28 | 38 | 29
| Mapping |  |  |  | 47.5%
| Figure Out Ideal Mapping Algorithm to use on Drone | N/A | Team | Mapping | 100% | 2021-01-13 | 2021-01-22 | 2021-02-06 | 25 | 10
| Have Drone virtually set up to map in virtual environment | 5 | Brennan/Ben | Mapping | 90% | 2021-02-20 | 2021-03-22 | 2021-04-01 | 41 | 31
| Use Data from Machine Learning Algorithm for heading control | 1 | Nathan/Joseph | Mapping | 0% | 2021-03-21 | 2021-04-04 | 2021-04-11 | 22 | 15
| Test out Drone Mapping and Saving | 1 | Team | Mapping | 0% | 2021-03-30 | 2021-04-23 | 2021-04-26 | 28 | 25
| Documents and Presentations |  |  |  | 75%
| First Draft of Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-01-04 | 2021-01-16 | 2021-01-18
| Plan of Action/ Current Status Report | N/A | Team | Documents/Presentations | 100% | 2021-01-14 | 2021-01-19 | 2021-01-19 | 6 | 6
| Initial Presentation for Projects 2 | N/A | Team |  | 100% | 2021-01-19 | 2021-01-21 | 2021-01-21
| Weekly Memo | N/A | Team | Documents/Presentations | 100% | 2021-01-22 | 2021-01-28 | 2021-01-28 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-01-25 | 2021-01-25 | 2021-01-25
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-01-28 | 2021-02-03 | 2021-02-03
| Weekly Progress Presentation | N/A | Brennan | Documents/Presentations | 100% | 2021-01-29 | 2021-02-04 | 2021-02-04 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-02-01 | 2021-02-01 | 2021-02-01
| Weekly Progress Report | N/A | Joseph | Documents/Presentations | 100% | 2021-02-04 | 2021-02-10 | 2021-02-10
| Weekly Progress Presentation | N/A | Joseph | Documents/Presentations | 100% | 2021-02-05 | 2021-02-11 | 2021-02-11 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-02-08 | 2021-02-08 | 2021-02-08
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-02-11 | 2021-02-17 | 2021-02-17
| Weekly Progress Presentation | N/A | Natthan | Documents/Presentations | 100% | 2021-02-12 | 2021-02-18 | 2021-02-18 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-02-15 | 2021-02-15 | 2021-02-15
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-02-18 | 2021-02-24 | 2021-02-24
| Weekly Progress Presentation | N/A | Ben | Documents/Presentations | 100% | 2021-02-19 | 2021-02-25 | 2021-02-25 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-02-22 | 2021-02-22 | 2021-02-22
| Weekly Memo | N/A | Brennan | Documents/Presentations | 100% | 2021-02-26 | 2021-03-04 | 2021-03-04 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-03-01 | 2021-03-01 | 2021-03-01
| Mid-Term Design Review (Report) | N/A | Team | Documents/Presentations | 100% | 2021-02-24 | 2021-03-07 | 2021-03-09
| Mid-Term Design Review (Presentation) | N/A | Team | Documents/Presentations | 100% | 2021-02-24 | 2021-03-05 | 2021-03-09
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-03-08 | 2021-03-08 | 2021-03-08
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-03-11 | 2021-03-17 | 2021-03-17
| Weekly Progress Presentation | N/A | Joe | Documents/Presentations | 100% | 2021-03-12 | 2021-03-18 | 2021-03-18 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-03-15 | 2021-03-15 | 2021-03-15
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-03-18 | 2021-03-24 | 2021-03-24
| Weekly Progress Presentation | N/A | Nathan | Documents/Presentations | 100% | 2021-03-19 | 2021-03-25 | 2021-03-25 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-03-22 | 2021-03-22 | 2021-03-22
| Weekly Progress Report | N/A | Team | Documents/Presentations | 100% | 2021-03-25 | 2021-03-31 | 2021-03-31
| Weekly Progress Presentation | N/A | Ben | Documents/Presentations | 100% | 2021-03-26 | 2021-04-01 | 2021-04-01 | 7 | 7
| Revise Gantt Chart | N/A | Team | Documents/Presentations | 100% | 2021-03-29 | 2021-03-29 | 2021-03-29
| Finalize Gantt Chart | 5 | Team | Documents/Presentations | 0% | 2021-04-05 | 2021-04-05 | 2021-04-20
| Client/Sponsor Presentation | 5 | Team | Documents/Presentations | 0% | 2021-04-09 | 2021-04-13 | 2021-04-30
| Final Report | 5 | Team | Documents/Presentations | 0% | 2021-04-01 | 2021-04-23 | 2021-04-30 | 30 | 23
| Final Presentation | 5 | Team | Documents/Presentations | 0% | 2021-04-01 | 2021-04-23 | 2021-04-30 | 30 | 23
| Final Poster | 5 | Team | Documents/Presentations | 0% | 2021-04-15 | 2021-04-23 | 2021-04-30
| RoboBoat Technical Design Report | 5 | Team | Documents/Presentations | 0% | 2021-04-20 | 2021-05-14 | 2021-05-23 | 34 | 25
| - Create the Plan for what to talk about in this TDR | 5 |  |  | 0% | 2021-04-20 | 2021-04-23 | 2021-04-25
| - Have First Draft made | 5 |  |  | 0% | 2021-04-20 | 2021-04-27 | 2021-05-03
| - Should be complete with all the formatting issues resovled | 5 |  |  | 0% | 2021-05-03 | 2021-05-12 | 2021-05-14
| RoboBoat ASV/UAV Video | 5 | Team | Documents/Presentations | 0% | 2021-04-20 | 2021-05-14 | 2021-05-23 | 34 | 25
| - Video 1: Power Management | 5 | Two - Three People |  | 0% | 2021-05-03 | 2021-05-12 | 2021-05-14
| * Create a checklist on what to present in this video | 5 |  |  | 0% | 2021-04-20 | 2021-04-23 | 2021-04-25
| * Create first draft of Video | 5 |  |  | 0% | 2021-04-20 | 2021-04-27 | 2021-05-03
| * Create full video and present to Dr. Vaughan by this date | 5 |  |  | 0% | 2021-05-03 | 2021-05-12 | 2021-05-14
- Video 2 | - Video 2: Sensor Optimization | 5 | Two - Three People |  | 0% | 2021-05-03 | 2021-05-12 | 2021-05-14
| * Create a checklist on what to present in this video | 5 |  |  | 0% | 2021-04-20 | 2021-04-23 | 2021-04-25
| * Create first draft of Video | 5 |  |  | 0% | 2021-04-20 | 2021-04-27 | 2021-05-03
| * Create full video and present to Dr. Vaughan by this date | 5 |  |  | 0% | 2021-05-03 | 2021-05-12 | 2021-05-14
Insert new rows ABOVE this one
Formulas:
In Progress = [In Progress, row below]
Note on B88: Author: Engineering reasoning will be needed Possibly Carbon Fiber
Note on B101: Author: Do we want to install Noetic or Kinetic
Note on B103: Author: Dr. Vaughan will have something for us in the next few days, Rotors, Darpa
Note on B109: Author: Should be one of the concentrations for a student worker or our Team later on in the weeks if available
Note on B155: Author: We will need to find a way to get access to the Rec Center as well as permission to do this on campus. This date is roughly when we should be able to test out the ASV and Drone.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.